Christopher Bero
Homework 6
CPE 495

Teamwork Skills and Project Management Strategies

Explain the difference between cross-functional and multi-disciplinary teams.
1. Identify the characteristics of the forming, storming, norming and performing stages in team development.
2. Describe the distinction between teams and teamwork.
3. According to the “Teams and Teamwork” chapter of the text, it is difficult to develop a consensus as the number of team members increases. Consider the situation where a team needs to agree on a proposal. Furthermore, assume that each team member's vote is random, with a 50% chance of agreeing with the proposal. Plot the probability of the team unanimously agreeing to the proposal versus the number of team members. Consider team sizes from 2 to 10. Overlay three additional plots for the situation where each team member has a 75%, 90% and 99% chance of agreeing to the proposal.
4. In your own words, describe what is meant by the term Work Breakdown Structure.
5. Consider the set of activities, duration (in days), and predecessors for a project given below.
Activity	A	B	C	D	E	F	G	H	I
Duration	3	9	6	6	6	3	2	6	7
Predecessors				A,B	D,B	C	F,E	G	F

1. a) Develop a network diagram representation for the project
2. b) Determine the critical path.
3. c) Determine the float time for all activities that are not on the critical path.
4. Explain why a network diagram cannot contain cycles (where a cycle is defined to be a sequence of activities where you can travel back to an activity already visited).
5. Describe the advantages and disadvantages of the network diagram and Gantt chart representation of a project. Identify the situations that would favor one over the other?